## Sheet1
S.No | Concern | Action | Raised By | Target Date | Remarks
1 | Power getting user not visible in permit system resulting due in permit closer | Developer will see these point in his server and will update accordingly. | EI&A | 15.10.24
2 | During downloading of SOP error massage reflect.
3 | No provision for working agency to check permit issuing status
4 | Need Isolation required check box for every job (Whether required or not) | Will be done by developer | Mechanical + EI&A
5 | Expaire date showing for JCAPCPL employee gatepass validity | Will be checked by developer and will be rectified accordingly. | Mechanical
6 | Suggested: If Raised permit not attended more then 24 hrs,its need to be stored in seprate Bin with reminder to the concern person for further action | Will be done by developer
7 | All data(Gatepass no,name etc) for contract worker not showing in auto feed | Will be checked by developer and will be rectified accordingly.
8 | At the time of renew permit ,raised renew permit not visible to issuer | Will be checked by developer and will be rectified accordingly.
9 | Master list adding facilities need to be incorporate in App | Will be done by developer
10 | At the time of permit renewal,after submitting an error pup up showing. | Will be checked by developer and will be rectified accordingly.
11 | When the requestor raises the permit and sends it to the working agency,after the permit leaves the working agency,they are unaware of where the permit has gone,which leads to delays in obtaininig the permit. | JCAPCPL: Previously, the requestor had to specify a particular name in the issuer agency field. However, after recent change, it now display department wise, allowing the permit to be sent to all issuers with the specific department , ensuring quicker issuance. (Issuer list will be shared to all function to know who are their issuers) | Operation (Utility) - GAPSPL |  | Jcapcpl Points
12 | Digital signature should be show for working agency & requestor. | Will be done by developer | Operation (Utility) - Nalco |  | No to Done Discussed in meeting
13 | TBT,PPE's checklist and hot work checklist uploading provision need to be provided in mobile application. | Will be done by developer | Operation (Utility)
13 | In permit system mechanical Isolation part not showing | Will be checked by developer and will be rectified accordingly. | Operation (Utility) - GAPSPL
14 | Instead of downloading permit it should be preview option first | Will be done by developer | Engg. & Projects
15 | Nomenclature need to be change from location and job location | Will be done by developer
16 | Permit renew issue araises in mobile application | Will be done by developer
17 | For renew purpose department drop down option need to be added | Will be done by developer
18 | In dash board permit close tab need to be incorporate | Will be done by developer